## CAP Umbrella Policies
Umbrella Policies for Climate Action Plan (CAP)
Proposed Policies |  | Comments
UMB1 | Target: Carbon neutrality by 2040 (This would amend the 2009 Master Plan carbon neutrality target date of 2030, which is infeasible given the fact that the Plan was never implemented given its almost immediate suspension and the fact that the Plan did not include commute emissions) | 2009 Master plan included carbon neutrality date of 2030. May not have included Scope 3 emissions (commuting). Plan was not implemented. Date does not appear viable.
UMB2 | Responsible parties will report annually on progress to meet carbon neutrality goals
UMB3 | Carbon Management Hierarchy: Consistent with Second Nature's guidance for the development and implementation of climate action plans, the priority order for emissions is (1) reduce emissions with energy efficiency and conservation, (2) replace carbon energy sources with renewable energy, (3) neutralize emissions with offsets | This is the prescribed approach under the president's carbon commitment.
UMB4 | The University will review, revise if necessary, and submit the climate action plan to Second Nature no less frequently than every five years
UMB5 | Annually the University will complete an evaluation of progress and submit to Second Nature
UMB6 | Integrate Climate Action Planning into other campus policies: e.g. Master Plan
UMB7 | The university will take a life-cycle planning approach to major projects.
UMB8 | Leverage partnership opportunities to reduce GHG emissions at least cost and greatest benefit (e.g. with the CSU, the City of Hayward, the County of Alameda) | e.g. East Bay Community Choice Energy, Power Purchase Agreements negotiated through the CSU

## ACTION BY DIVISION
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
Division | Department | Action Step | Establishment Timeline (*) | Key
CA | Campus Administration | ENG4 | Near term | CA | Campus Administration (all divisions - AA, FA, SA, UA, and Diversity, Leadership & Employee Wellness)
|  | ENG5 | Near term | AF | Administration & Finance
|  | TRAN10 | Near term | AA | Academic Affairs
|  | HOUS2 | Long term | SA | Student Affairs
|  | HOUS3 | Near term | ENG | Energy
AF | Administration & Finance | TRAN4 | Near term | TRAN | Transportation
|  | TRAN6 | Near term | BLDG | Buildings
|  | FIN1 | Near term | HOUS | Housing
|  | FIN2 | Near term | PROC | Procurement
AF | Accounting | OFF1 | Near term | LAND | Landscaping
AF | Education Foundation Board of Directors | FIN4 | Near term | EDU | Education
AF | Facilities | ENG1 | Near term | FIN | Finance
|  | ENG2 | Immediate to long term | OFF | Offsets
|  | ENG3 | Immediate to long term | *Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).
|  | ENG4 | Near term
|  | ENG5 | Near term
|  | ENG6 | Immediate
|  | ENG9 | Medium term
|  | TRAN7 | Immediate
|  | BLDG1 | Immediate
|  | BLDG2 | Near term
|  | BLDG3 | Long term (sustained effort through 2040)
|  | BLDG4 | Immediate
|  | BLDG5 | Near term
|  | BLDG6 | Near term
|  | HOUS1 | Near term
|  | LAND1 | Near term
|  | LAND2 | Near term
|  | LAND3 | Immediate
|  | LAND4 | Near term
|  | LAND5 | Medium to long term
|  | LAND6 | Immediate
|  | LAND7 | Near to medium term
|  | LAND8 | Near to medium term
|  | LAND9 | Near term
|  | FIN3 | Immediate
AF | Institutional Technology | ENG7 | Near term
|  | TRAN1 | Immediate to long term
AF | Procurement | TRAN9 | Immediate
|  | BLDG2 | Near term
|  | BLDG3 | Long term (sustained effort through 2040)
|  | PROC1 | Immediate
|  | PROC2 | Near term
|  | PROC3 | Near term
|  | PROC4 | Immediate
|  | PROC5 | Near term
AA | Academic Affairs | TRAN1 | Immediate to long term
|  | LAND8 | Near to medium term
|  | EDU5 | Immediate to long term
AA | Academic Senate | EDU1 | Medium term
|  | EDU3 | Immediate
|  | EDU4 | Near term
AF/AA | Campus Sustainability Committee | LAND2 | Near term
|  | OFF1 | Near term
AA | Center for Community Engagement | EDU2 | Near term
AA | Faculty | ENG8 | Near term
|  | EDU2 | Near term
AA | University Extension | TRAN5 | Near term
AA | Sustainability | EDU2 | Near term
SA | Admissions | TRAN5 | Near term
SA | Transportation | TRAN2 | Immediate
|  | TRAN3 | Near term
|  | TRAN8 | Near term to long term

## ENERGY
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
ENERGY
ENERGY |  | Est. Impact | Leadership | Est. Resources | Establishment Timeline (*)
ENG1 | Develop and maintain an operation and maintenance plan to reduce energy use, maximize equipment efficiency, and most effectively utilize deferred maintenance funds. (The Campus will prioritize facilities upgrades that reduce operating costs and replace equipment at end of life. The campus energy team will engage in an ongoing process to seek opportunities to improve energy efficiency using energy monitoring data, periodic energy audits, continuous commissioning) | Significant GHG reduction potential; significant operational cost savings | Facilities | Staff time (high initially, tapering to moderate) | Near term
ENG2 | Install 680 kW of new PV, or other renewable energy capacity annually (or acquire 1.2 million kWh more of RE from the power grid each year, or some combination of the two) | Significant GHG reduction potential; potentially cost neutral | Facilities | Staff time (moderate and sustained) | Immediate to long term
ENG3 | Prioritize PV installations to: displace all Concord Campus Energy use (~630kW), on Hayward Campus parking lots (~8MW long term) | Significant GHG reduction potential | Facilities | Staff/consultant time (moderate) | Immediate to long term
ENG4 | Install PV system of a size necessary to displace annual electricity use of the Concord Campus | Very significant GHG reduction potential; low to moderate equipment cost with potential for RECs; significant educational opportunity | Admin, Facilities | Staff time (moderate) | Near term
ENG5 | Prioritize purchase of high renewable powercontent, low unspecified power content, grid power. Pursue possibility of aggregated group purchase of off-site renewable energy with other CSU campuses, the City of Hayward, or the County of Alameda | Significant GHG reduction potential; cost of power may be higher than current contract in the near term | Admin, Facilities | Staff/consultant time (low to moderate) | Near term
ENG6 | Institute on-going energy management training of building technicians | Significant operational cost savings and GHG reduction potential | Facilities | Staff time (moderate) | Immediate
ENG7 | The campus information technology team will maintain all campus-owned computers, displays, and related technology to always operate in energy saver mode, unless needed for a documented exception. | Low to moderate operational cost savings and GHG reduction potential | IT | Staff time (low) | Near term
ENG8 | Research emerging energy technologies for carbon savings (e.g. PV-source heat pump replacing natural gas, thermal energy storage) | Possibly significant GHG reduction potential | Faculty | Faculty-student research time; potential significant cost | Near term
ENG9 | Investigate the potential for Cal State East Bay wind-power facilities | Low to moderate GHG reduction potential; moderate educational value | Facilities | Faculty-student research time | Medium term
*Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).

## TRANSPORTATION
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
TRANSPORTATION |  | Est. Impact | Leadership | Est. Resources | Establishment Timeline (*)
TRAN1 | Increase online coursework and opportunities for telework | Significant GHG reduction potential | Academic Affairs and IT | Staff time (moderate), Software cost and maintainence cost (low), Co-benefits (high) | Immediate to long term
TRAN2 | Enhance and encourage the use of alternative transportation modes | Significant GHG reduction potential | Transportation Planning | Staff time (low to moderate incremental cost) | Immediate
TRAN3 | Pursue subsidized transit passes for students, staff, and faculty (including AC transit and BART) | Moderate to significant GHG reduction potential | Transportation Planning | Staff time (moderate) | Near term
TRAN4 | Encourage the use of alternative transportation modes with faculty and staff by implementing an Employee Cash Out Program (offer cash instead of a subsidized parking pass) | Moderate GHG reduction potential; low cost depending on the conditions of the plan; potential employee co-benefits (health, financial, job satisfaction) | Finance and Administration | Staff time (low, incremental initial investment) | Near term
TRAN5 | Offset carbon emissions from all study abroad and international travel by 2022: investigate adding the cost to the program fee that covers carbon emissions from airfare to and from the origin/destination city. | Moderate to significant GHG reduction potential; no cost implications | Admissions, University Extension | Staff time (low) | Near term
TRAN6 | All state-funded travel will be carbon neutral or 100% offset by 2022 | Low GHG reduction potential; but more predicable outcome than most transportation measures and high education value for the university community | Administration and Finance | Staff time (low cost) | Near term
TRAN7 | No net increase in the number of parking spaces for fossil-fueled vehicles. | Moderate GHG emissions reduction potential | Facilities | Staff time (no cost) | Immediate
TRAN8 | Maintain at least 50% greater EV charging station capacity (relative to total number of parking spaces) than the statewide EV vehicle proportion as reported by the state. So, for example, if 10% of the state's onroad fleet is EVs, then 15% or our parking spaces will be for EVs. | Low to moderate GHG reduction potential; potential educational value | Parking | Staff time (moderate), utilize grants for EV changing stations | Near term to long term
TRAN9 | All new-to-campus fleet vehicles must be electric, bio-fueled, or other RE-powered | Low GHG reduction, reduced operational costs | Procurement | Potentially higher initial cost | Immediate
TRAN10 | No personal vehicle/parking passes for first year residence hall students: supplement with electric or other ultra-efficient car-share vehicles | Low direct GHG reduction potential but sets the habit of becoming more comfortable with relying on alternative transportation | Admin | Staff time (low) | Near term
*Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).
[1] Employee Cash Out Program: https://www.bestworkplaces.org/pdf/ParkingCashout_07.pdf. https://www.arb.ca.gov/planning/tsaq/cashout/cashout.htm May also aid in compliance with Commuter Benefit Program SB1128: (http://assets.511.org/pdf/nextgen/commuter-benefits/Program_Overview.pdf)"

## BUILDINGS
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
BUILDINGS |  | Est. Impact | Leadership | Est. Resources | Establishment Timeline (*)
BLDG1 | Design all new buildings to be Zero Net Energy (ZNE) starting immediately. The design process will consider the criteria and potential certification under the following: LEED, Living Building Challenge, Passive House Institute US | Significant operational cost savings and GHG reduction potential over lifetime of building | Facilities | Staff/consultant time (significant initial) | Immediate
BLDG2 | No new natural-gas consuming equipment for space and water conditioning starting in 2022. For example, solar thermal systems, PV-driven heat pump systems, or off-set. | Significant GHG reduction potential | Facilities and Procurement | Staff time (moderate initial); likely higher initial cost | Near term
BLDG3 | Replace space heating, water heating, and cooking equipment with ultra efficient fossil-fuel-free technologies (e.g. heat pump technology) | Significant GHG reduction potential | Facilities and Procurement | Staff time (moderate initial); likely higher initial cost | Long term (sustained effort through 2040)
BLDG4 | Maximize PV production on all new buildings. | Moderate GHG reduction potential, cost savings over lifetime of system | Facilities | Staff/consultant time (moderate initial) | Immediate
BLDG5 | Track building energy performance with computerized monitoring systems (building energy-use monitoring) to enable more effective building energy management and GHG emissions reductions tracking [1] | Moderate GHG reduction potential, moderate operational cost savings from more effective energy use | Facilities | Staff/consultant time (moderate initially, low later) | Near term
BLDG6 | Post climate action educational display prominently in all main buildings. Signage will state Cal State East Bay's climate neutrality goal, and graphically display the building's progress thereto, starting with the baseline monitoring year. Longer term goal to incorporate real-time dashboard of overall GHG savings on main buildings | Significant educational and motivational impact | Facilities | Staff time (low) | Near term
*Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).
[1] CSUEB is installing an energy management system for Science N and S, SF, and SA. This represents the first of EMS at CSUEB. We plan to expand that to all buildings and the Concord Campus. We plan for completion by 2020 ... If possible, can this also be segmented within buildings. For example, in the UUs, it would be great to differentiate energy use by dining services as opposed to other functions within the building (Martin). Project for future group.; Energy monitoring with Envt/Physics class per R. Smith looking at lighting, plug loads

## HOUSING
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
HOUSING |  | Est. Impact | Leadership | Est. Resources | Establishment Timeline (*)
HOUS1 | Switch to Solar Water Heating in Pioneer Heights. Investigate options (solar thermal collectors versus PV). | Significant reduction in natural gas demand in residence halls and associated GHG reductions (currently N-gas accounts for 60% of the Hayward Campus's residence hall energy use.) | Facilities | Moderate up-front cost | Near term
HOUS2 | Institute policy to increase campus housing to 5,000 student residents by 2032 and encourage first year students to live in residence halls (consistent with master plan) | Significant GHG reduction potential from both commuting and zero net energy housing, but increases the challenge of achieving carbon neutrality; potential increase in water use on campus | Admin | Staff/consultant time (significant); high cost | Long term
HOUS3 | Investigate potential for building low-cost faculty housing on or near campus. Co-benefit of attracting qualified faculty on state salary given prohibitive Bay Area housing prices | Moderate GHG reduction potential from commuting and zero net energy housing, but increases the challenge of achieving carbon neutrality; potential increase in water use on campus; potentially significant co-benefits in attracting and retaining new faculty | Admin | Staff/consultant time (significant); high cost | Near term
*Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).

## PROCUREMENT
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
PROCUREMENT |  | Est. Impact | Leadership | Est. Resources | Establishment Timeline (*)
PROC1 | Adopt Electronics and Appliance Procurement Policy (in progress) that requires: Bronze EPEAT® or higher for EPEAT®-rated products, ENERGY STAR® for everything else if available, and Suppliers to deliver electronics with conservation and energy efficiency features enabled and as the auto-default | Moderate GHG reduction potential, moderate operational cost savings | Procurement | Staff time (low) | Immediate
PROC2 | Initiate accounting of carbon emissions from procurement (e.g. using the Economic Input-Output Life Cycle Assessment (EIP-LCA) tool) | Significant GHG reduction potential | Procurement | Staff time (significant initially to low in the long term) | Near term
PROC3 | Investigate policy for locally sourcing materials to reduce transportation energy use associated with procurement. E.g. Purchase majority of construction materials within 250 miles | Moderate GHG reduction potential, potential for higher cost of goods | Procurement | Staff time (low) | Near term
PROC4 | Establish 100% Recycled Copy/Print Paper Policy (in progress) | Low GHG reduction potential; increased cost of paper | Procurement | Staff time (insignificant) | Immediate
PROC5 | Continue to move away from the use of paper-based processes with digital processes | Low GHG reduction potential; moderate monetary cost savings potential | Procurement | Staff time (initial investment high) | Near term
*Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).
[1] http://www.eiolca.net/

## LANDSCAPING
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
LANDSCAPING |  | Est. Impact | Leadership | Est. Resources | Establishment Timeline (*)
LAND1 | The university will adopt SITES certification criteria in developing landscaping projects | Moderate general environmental benefits | Facilities | Staff time (low) | Near term
LAND2 | The university will adopt Bay Friendly Landscaping practices | Moderate operational cost savings from energy, water, and labor reductions; moderate GHG reduction potential; environmental benefits. | Facilities, CSC | Staff time (high initial, then low) | Near term
LAND3 | University will discontinue use of synthetic fertilizers within 5 years | Minimal GHG emissions reduction, moderate general environmental and health benefits, significant symbolic impact | Facilities | Staff time (low) | Immediate
LAND4 | Newly purchased equipment to be electric, battery-powered, biofueled, or other RE-powered when commercial grade equipment is available | Operational cost savings from reduced equipment maintenance, low GHG reduction potential, potential health benefits | Facilities | Staff time (low) | Near term
LAND5 | Carbon sequestration: Restore native woodland to maximum extent possible on non-landscaped areas of the Hayward and Concord campuses. | Significant ecological benefits, moderate GHG reductions; Cost implications need to be studied (possible cost benefits if offsets from sequestration are certified) | Facilities | Staff time (significant) | Medium to long term
LAND6 | Continue turf conversion project using Bay Friendly Landscaping policies. | Operational cost savings from energy, water, and labor savings; environmental benefits. | Facilities | Staff time (moderate) | Immediate
LAND7 | Increase tree cover in parking lots and other locations on campus. Use high albedo paving surfaces (permeable where possible). | Moderate GHG reduction potential; significant co-benefits including mitigation of heat island effect, positive aesthetic impact; significant environmental comfort and health benefits | Facilities | Monetary cost (moderate initial cost) | Near to medium term
LAND8 | Pursue the development of on-campus organic food production in the form of multi-cultural heritage gardens, that serve as a foundation for the sharing of multicultural food and traditions. | Minimal GHG reduction potential; significant co-benefits | Academic Affairs, Facilities | Staff and faculty time (2 FTE) Moderate initial cost | Near to medium term
LAND9 | Continue to investigate the potential for on-campus composting program consisting of food waste and landscape debris with finished product for reuse as compost, landscape materials on campus. | Low GHG reduction resulting from decreased transport of materials to waste facility and decrease in need for synthetic fertilizer; operational cost savings as finished compost used in place of purchased fertilizer | Facilities | Staff time, additional staffing may be needed | Near term
*Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).
[1] http://rescapeca.org
[2] 50-93% water savings, up to 70% reduced maintenance time, up to 48.5 MTeCO2/acre-yr (http://www.stopwaste.org/preventing-waste/bay-friendly-basics) • Water-related energy use consumes 20% of the State of California's electricity demand, and landscape-related water use comsumes 50% of state's water resources. (https://www3.epa.gov/region9/waterinfrastructure/waterenergy.html)

## EDUCATION
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
EDUCATION AND FACULTY DEVELOPMENT |  | Est. Impact | Leadership | Est. Resources | Establishment Timeline (*)
EDU1 | Pursue fulfillment of commitment to educate all students on carbon neutrality (per the 2007 Senate Sustainability Resolution and the President's Carbon Commitment) | Highly significant educational impact. Moderate direct GHG reduction potential, but possibly large indirect GHG reductions through changing students behaviors and attitutudes over their lifetime. | Academic Senate | Transition cost in faculty time developing courses that embed carbon neutrality into GE offerings; Academic Senate time for developing learning outcomes for carbon neutrality coursework | Medium term
EDU2 | Facilitate student learning on climate neutrality issues through involvement in research, hands-on-learning, campus-as-a-living-laboratory, community engagement on issues of climate mitigation and adaptation, carbon-neutrality internship placements, and freshman learning communities | Significant educational impact, especially for diverse student population, as under-represented minorities benefit most from high impact learning practices such as theses. Significant GHG reduction potential from campus-as-living-laboratory projects. | Faculty, Office of Sustainability, Center for Community Engagement | Faculty time (incremental cost) | Near term
EDU3 | Include recognition of work on University ILOs in the RTP process (this indirectly supports carbon neutrality work through the Sustainability ILO) | Moderate | Academic Senate | Insignificant marginal effort | immediate
EDU4 | Pursue an interdisciplinary sustainability minor that includes education on carbon neutrality | Moderate but important stepping stone | Academic Senate | Moderate | near term
EDU5 | Pursue faculty hires to support universal education on carbon neutrality | Significant and essential to maintain momentum | Academic Affairs | Insignificant (faculty will need to be hired regardless) | immediate to long term
*Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).

## FINANCE
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
FINANCE |  | Est. Impact | Leadership | Est. Resources | Establishment Timeline (*)
FIN1 | Financial Analysis of Carbon Neutrality Plan An analysis of the most cost effective to achieve carbon neutrality, to account for and prioritize projects based on project implementation costs, potential long-term financial costs/benefits, and greenhouse gas reductions | Significant: Enabler of entire Climate Action Plan | Administration and Finance Division | Staff time (significant initial investment) | Near term
FIN2 | Ensure Annual Budget & Staff Time for GHG-reduction efforts. Best practices include the use of an energy efficiency revolving fund in which costs savings resulting from energy efficiency improvements are reinvested in further improvements | Significant GHG reduction impact in that this enables fulfillment of the Climate Action Plan; potentially significant energy cost savings from energy efficiency projects | Administration and Finance Division | Staff time (moderate investment) | Near term
FIN3 | Incorporate the cost of carbon, along with other project costs, in the cost-benefit analysis of new infrastructure projects: Use the most recent mean price (dollars per metric ton) from the California Cap-and-Trade Program Auction. Currently available in the Summary of Results Report on the California Air Resources Board website: https://www.arb.ca.gov/cc/capandtrade/auction/auction.htm#proceeds | Significant educational impact for staff because it serves as constant reminder to incorporate carbon neutrality in all project planning. Moderate GHG reduction potential | Facilities | Staff time (low incremental cost) | Immediate
FIN4 | Divest from fossil fuel investments: (focused on companies with major investments in coal, oil, gas, and/or unconventional fossil fuels (e.g. oil shale and tar sands). Co-benefit: prudent to protect the university from excessive volatility in fossil energy prices. (see for example NYT, 3-10-2017) Amend the Cal State East Bay Education Foundation Investment Policy accordingly | Significant educational and ethical impact. Important PR messaging impact. Moderate GHG reduction potential because of small endowment currently. Potential longer-term higher investment returns given the global shift toward alternative sustainable energy sources | Cal State East Bay Education Foundation Board of Directors | Staff time (low) | Near term
*Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).

## OFFSETS
ACTION STEPS (PRIORITIZED)
CSUEB 2018 CLIMATE ACTION PLAN MEASURES - SUMMARY
OFFSETS |  | Est. Impact | Leadership | Est. Resources | Establishment Timeline (*)
OFF1 | True-up Emissions Policy. To ensure emissions reduction efforts meet targets the University will assess and true-up emissions every three years and make offset purchases as needed to meet with target. [1] | Significant GHG reduction potential; monetary cost savings, because offsets are only used to help achieve emissions reductions targets if the offsets cost are lower than achieving those same reductions through efficiency improvements or renewable energy. | CSC, Accounting | Staff time (insignificant incremental cost beyond the annual GHG inventory, which must be conducted regardless) | Near term
*Establishment Timeline is defined as follows: Immediate (2018); Near term (by 2025); Medium term (by 2030); Long term (by 2040).
[1] "PROJECTS • CSUEB Oak Woodland Restoration: restore nonnative grasslands to native woodlands/grasslands. (Use of compost in grasslands would further carbon sequestration potential.) Investigate the potential to certify as an offset. • Hayward Shoreline Wetland Restoration • Discovery Gardens, crabapple grafting, sensory or tactile gardens Dr. Patty Oikawa is a carbon sequestration expert with extensive experience in wetland restoration of Hayward Shoreline."
3 | High level action consisting of…..

## TEMPLATE
ACTION STEPS
CSUEB 2018 CLIMATE ACTION PLAN MEASURES- SUMMARY
CATEGORY |  | Est. Resources | Est. Impact | Leadership
1 | Require, build, institute High level action consisting of….. | Staff time, moderate investment, high cost, rebate avail to cover some costs, depending on design, | <1%, 2-5%, measurable, significant GHG reduction | Facilities, IT, Admin, Proc, Assoc Students, Acct, CSC
2 | High level action consisting of…..
3 | High level action consisting of…..
4 | High level action consisting of…..
5 | High level action consisting of…..
6 | High level action consisting of…..
7 | High level action consisting of…..
8 | High level action consisting of…..
9 | High level action consisting of…..
10 | High level action consisting of…..