## CAP Action Steps May 18-19
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
ENG1 | Develop and maintain an operation and maintenance plan to reduce energy use, maximize equipment efficiency, and most effectively utilize deferred maintenance funds. (The Campus will prioritize facilities upgrades that reduce operating costs and replace equipment at end of life. The campus energy team will engage in an ongoing process to seek opportunities to improve energy efficiency using energy monitoring data, periodic energy audits, continuous commissioning) | In Progress | Significant GHG reduction potential; significant operational cost savings | Facilities | Near Term (by 2025) | Facilities Development & Operations is working within the Division of Administration and Finance to complete a Request for Purchase (RFP) to select a vendor to conduct an energy efficiency assessment for CSUEB. Energy assessment will provide a baseline of energy use and be used to assess savings for Solar IV
ENG2 | Install 680 kW of new PV, or other renewable energy capacity annually (or acquire 1.2 million kWh more of RE from the power grid each year, or some combination of the two) | In Progress | Significant GHG reduction potential; potentially cost neutral | Facilities | Immediate (2018) to Long Term (by 2040) | Facilities Development & Operations is working within the Division of Administration & Finance and the Chancellor's Office on Solar IV: System-Wide Solar Photovoltaic Program Master Enabling Agreement (MEA) at CSU East Bay.
ENG3 | Prioritize PV installations to: displace all Concord Campus Energy use (~630kW), on Hayward Campus parking lots (~8MW long term) | Yet to be addressed | Significant GHG reduction potential | Facilities | Immediate (2018) to Long Term (by 2040)
ENG4 | Install PV system of a size necessary to displace annual electricity use of the Concord Campus | Yet to be addressed | Very significant GHG reduction potential; low to moderate equipment cost with potential for RECs; significant educational opportunity | Facilities,Admin | Near Term (by 2025)
ENG5 | Prioritize purchase of high renewable powercontent, low unspecified power content, grid power. Pursue possibility of aggregated group purchase of off-site renewable energy with other CSU campuses, the City of Hayward, or the County of Alameda | In Progress | Significant GHG reduction potential; cost of power may be higher than current contract in the near term | Facilities,Admin | Near Term (by 2025) | CSU East Bay Housing has been converted to East Bay Community Energy (EBCE), a local electricity provider that procures electricity from clean, renewable sources such as solar and wind. "EBCE reinvests earnings back into the community to create local green energy jobs, local programs, and clean power projects."
ENG6 | Institute on-going energy management training of building technicians | Meeting Requirements | Significant operational cost savings and GHG reduction potential | Facilities | Immediate (2018) | Staff in facilities are trained in the daily operation, repair and maintenance of the several building management systems in each building. Energy management is achieved through the optimization and efficiency of mechanical, electrical and plumbing systems using defined programs controlling the following: HVAC equipment schedules Lighting schedules Low water volume plumbing fixtures Sprinkler schedules Solar panel support equipment maintenance Fuel Cell waste water On-going training attended is as follows: Certified Pool Operator certification Building Operator Certificate certification Chiller/Boiler training/certification Vendor specific building management training/certification Lighting Automation training
ENG7 | The campus information technology team will maintain all campus-owned computers, displays, and related technology to always operate in energy saver mode, unless needed for a documented exception. | In Progress | Low to moderate operational cost savings and GHG reduction potential | IT | Near Term (by 2025) | When computer monitors are configured they will typically go into energy saver mode after a period of non-usage. TV monitors used in classrooms and conference rooms are controlled by a single platform that will turn them off at night. Projectors in classrooms are turned off if not in use.
ENG8 | Research emerging energy technologies for carbon savings (e.g. PV-source heat pump replacing natural gas, thermal energy storage) | Yet to be addressed | Possibly significant GHG reduction potential | Faculty | Near Term (by 2025)
ENG9 | Investigate the potential for Cal State East Bay wind-power facilities | In Progress | Low to moderate GHG reduction potential; moderate educational value | Facilities | Medium Term (by 2030) | As part of Physics 3999 in Spring 2017 led by Dr. Ryan Smith, a wind monitoring study was done on North Science Building by students Michael Norcross & Michael Kronic which suggested average wind speeds did not meet the required wind speed to move a typical low wind speed turbine. Based on their collected data, they recommended the installation of solar panels be perused on Hayward Campus instead of wind turbines. Wind energy generation may be more feasible on Concord Campus.
TRAN1 | Increase online coursework and opportunities for telework | Yet to be addressed | Significant GHG reduction potential | Academic Affairs,IT | Immediate (2018) to Long Term (by 2040)
TRAN2 | Enhance and encourage the use of alternative transportation modes | In Progress | Significant GHG reduction potential | Transportation Planning | Immediate (2018) | An RFP for a new shuttle contract was issued in March 2019. The new shuttle contract allows the opportunity to add additional shuttles to meet higher ridership demands as needed. Bids received from the RFP will allow for better decision making on whether or not to continue using shuttles or switching service to AC Transit. Transportation has plans to increase collaboration with ASI. In order to promote alternative transportation programs as CSUEB, Transportation will table more often during U-hour. At tabling events, students will have the opportunity to sign up for alternative transportation programs in exchange for CSUEB swag.
TRAN3 | Pursue subsidized transit passes for students, staff, and faculty (including AC transit and BART) | In Progress | Moderate to significant GHG reduction potential | Transportation Planning | Near Term (by 2025) | Procurement is currently in discussions with AC Transit about AC Transit providing exclusive service to the Hayward campus. This would be free for students, faculty, and staff on all AC transit routes, including Transbay, 7 days per week. An RFP was issued for Shuttle Services (in the event that an agreement with AC Transit does not materialize). Responses are due back at the end of April 2019, and will be evaluated. It is expected that by July 2019 CSU East Bay shall be able make the determination which one of the following three options are best for the campus: (i) Contracting with AC Transit, (ii) Awarding a contract for a shuttle provider, or (iii) Piggybacking off of a University of California Merced contract award and use the hourly rates established under that contract for CSU East Bay.
TRAN4 | Encourage the use of alternative transportation modes with faculty and staff by implementing an Employee Cash Out Program (offer cash instead of a subsidized parking pass) | Yet to be addressed | Moderate GHG reduction potential; low cost depending on the conditions of the plan; potential employee co-benefits (health, financial, job satisfaction) | Admin,Finance | Near Term (by 2025)
TRAN5 | Offset carbon emissions from all study abroad and international travel by 2022: investigate adding the cost to the program fee that covers carbon emissions from airfare to and from the origin/destination city. | Yet to be addressed | Moderate to significant GHG reduction potential; no cost implications | Admissions,University Extension | Near Term (by 2025)
TRAN6 | All state-funded travel will be carbon neutral or 100% offset by 2022 | In Progress | Low GHG reduction potential; but more predicable outcome than most transportation measures and high education value for the university community | Admin,Finance | Near Term (by 2025) | CSUEB's AY18/19 Climate Corps AmeriCorps Fellow has been researching and developing methods of offsetting GHG emissions resulting from Directly Financed Air Travel. In order to develop a policy recommendation for CSUEB, the Climate Corps Fellow has used Second Nature's Carbon Pricing Toolkit and researched programs that other Higher Ed Institutions are piloting where a cost of carbon is added to their business travel to offset the resulting emissions. The recommendation proposes a CSUEB Carbon Neutral State Funded Air Travel Policy, which includes assessing a minimal cost of carbon to all directly financed air travel and using the funds to either purchase verified carbon offsets, or reinvest the funds in on-campus projects that provide measurable reductions in GHG emissions. The research and proposal ideas were presented at the Campus Sustainability Committee meeting in April. Based on the positive feedback received, a policy recommendation is being drafted.
TRAN7 | No net increase in the number of parking spaces for fossil-fueled vehicles. | Meeting Requirements | Moderate GHG emissions reduction potential | Facilities | Immediate (2018) | In 2018 there have not been any additional parking spaces added on campus for fossil fueled vehicles.
TRAN8 | Maintain at least 50% greater EV charging station capacity (relative to total number of parking spaces) than the statewide EV vehicle proportion as reported by the state. So, for example, if 10% of the state's onroad fleet is EVs, then 15% or our parking spaces will be for EVs. | In Progress | Low to moderate GHG reduction potential; potential educational value | Parking | Near Term (by 2025) to Long Term (by 2040) | Hayward campus currently has 25 EV charging stations, which can accomodate 50 EVs, 50 EV parking spaces, and 10 EV waiting spaces. Lot A on Hayward campus is expecting to convert 5 parking spaces to EV waiting spaces and on Concord campus 4 EV charging stations are expected to be installed in Summer 2019.
TRAN9 | All new-to-campus fleet vehicles must be electric, bio-fueled, or other RE-powered | Yet to be addressed | Low GHG reduction, reduced operational costs | Procurement | Immediate (2018)
TRAN10 | No personal vehicle/parking passes for first year residence hall students: supplement with electric or other ultra-efficient car-share vehicles | Yet to be addressed | Low direct GHG reduction potential but sets the habit of becoming more comfortable with relying on alternative transportation | Admin | Near Term (by 2025)
BLDG1 | Design all new buildings to be Zero Net Energy (ZNE) starting immediately. The design process will consider the criteria and potential certification under the following: LEED, Living Building Challenge, Passive House Institute US | In Progress | Significant operational cost savings and GHG reduction potential over lifetime of building | Facilities | Immediate (2018) | In April 2019 CSUEB celebrated the groundbreaking of the CORE Building, which is being designed as a zero net energy ready building. Construction is slated for summer 2019 - summer 2021.
BLDG2 | No new natural-gas consuming equipment for space and water conditioning starting in 2022. For example, solar thermal systems, PV-driven heat pump systems, or off-set. | In Progress | Significant GHG reduction potential | Facilities,Procurement | Near Term (by 2025) | Chancellor's Office is discussing and developing guidance on eliminating natural gas use on campuses. We are awaiting guidance.
BLDG3 | Replace space heating, water heating, and cooking equipment with ultra efficient fossil-fuel-free technologies (e.g. heat pump technology) | Yet to be addressed | Significant GHG reduction potential | Facilities,Procurement | Long Term (by 2040)
BLDG4 | Maximize PV production on all new buildings. | Yet to be addressed | Moderate GHG reduction potential, cost savings over lifetime of system | Facilities | Immediate (2018)
BLDG5 | Track building energy performance with computerized monitoring systems (building energy-use monitoring) to enable more effective building energy management and GHG emissions reductions tracking [1] | In Progress | Moderate GHG reduction potential, moderate operational cost savings from more effective energy use | Facilities | Near Term (by 2025) | The Facilities Department has developed spreadsheets, using the baseline year of 2013 to evaluate progress made on eliminating GHG on campus. Facilities has continued to refine energy information received from the energy and building management systems to inform efficient building operations to meet the campus's GHG reduction goals.
BLDG6 | Post climate action educational display prominently in all main buildings. Signage will state Cal State East Bay's climate neutrality goal, and graphically display the building's progress thereto, starting with the baseline monitoring year. Longer term goal to incorporate real-time dashboard of overall GHG savings on main buildings | Yet to be addressed | Significant educational and motivational impact | Facilities | Near Term (by 2025)
HOUS1 | Switch to Solar Water Heating in Pioneer Heights. Investigate options (solar thermal collectors versus PV). | Yet to be addressed | Significant reduction in natural gas demand in residence halls and associated GHG reductions (currently N-gas accounts for 60% of the Hayward Campus's residence hall energy use.) | Facilities | Near Term (by 2025)
HOUS2 | Institute policy to increase campus housing to 5,000 student residents by 2032 and encourage first year students to live in residence halls (consistent with master plan) | Yet to be addressed | Significant GHG reduction potential from both commuting and zero net energy housing, but increases the challenge of achieving carbon neutrality; potential increase in water use on campus | Admin | Long Term (by 2040)
HOUS3 | Investigate potential for building low-cost faculty housing on or near campus. Co-benefit of attracting qualified faculty on state salary given prohibitive Bay Area housing prices | Yet to be addressed | Moderate GHG reduction potential from commuting and zero net energy housing, but increases the challenge of achieving carbon neutrality; potential increase in water use on campus; potentially significant co-benefits in attracting and retaining new faculty | Admin | Near Term (by 2025)
PROC1 | Adopt Electronics and Appliance Procurement Policy (in progress) that requires: Bronze EPEAT® or higher for EPEAT®-rated products, ENERGY STAR® for everything else if available, and Suppliers to deliver electronics with conservation and energy efficiency features enabled and as the auto-default | Meeting Requirements | Moderate GHG reduction potential, moderate operational cost savings | Procurement | Immediate (2018) | Draft policy is complete and in use on campus. Waiting on "Policy on policies" to formally adopt. Procurement has been incorporating a sustainability blurb in the P-card Policy. The sustainability blurb is a broad statement that covers multiple sustainable procurement sectors. Includes the following statement, "Ordering energy efficient electronics should be considered in all purchasing." The statement also directs the reader to CSUEB's Sustainability website.
PROC2 | Initiate accounting of carbon emissions from procurement (e.g. using the Economic Input-Output Life Cycle Assessment (EIP-LCA) tool) | Yet to be addressed | Significant GHG reduction potential | Procurement | Near Term (by 2025)
PROC3 | Investigate policy for locally sourcing materials to reduce transportation energy use associated with procurement. E.g. Purchase majority of construction materials within 250 miles | In Progress | Moderate GHG reduction potential, potential for higher cost of goods | Procurement | Near Term (by 2025) | Procurement has been incorporating a sustainability blurb in the P-card Policy. The sustainability blurb is a broad statement that covers multiple sustainable procurement sectors. Includes section that states the selection of vendors should consider distance and minimization of number of deliveries.
PROC4 | Establish 100% Recycled Copy/Print Paper Policy (in progress) | Meeting Requirements | Low GHG reduction potential; increased cost of paper | Procurement | Immediate (2018) | Draft policy is complete and in use on campus. Waiting on "Policy on policies" to formally adopt.
PROC5 | Continue to move away from the use of paper-based processes with digital processes | In Progress | Low GHG reduction potential; moderate monetary cost savings potential | Procurement | Near Term (by 2025) | CSUEB is in the process of implementing the fully electronic Certify Reimbursement System, which moves the reimbursement process completely away from paper processes. A pilot program will launch in April 2019 beginning with A & F, if it is successful this program will launch campus wide. CSUEB has adopted the Adobe Sign program, removing the need for paper signatures.
LAND1 | The university will adopt SITES certification criteria in developing landscaping projects | Yet to be addressed | Moderate general environmental benefits | Facilities | Near Term (by 2025)
LAND2 | The university will adopt Bay Friendly Landscaping practices | Yet to be addressed | Moderate operational cost savings from energy, water, and labor reductions; moderate GHG reduction potential; environmental benefits. | Facilities,CSC | Near Term (by 2025)
LAND3 | University will discontinue use of synthetic fertilizers within 5 years | Yet to be addressed | Minimal GHG emissions reduction, moderate general environmental and health benefits, significant symbolic impact | Facilities | Immediate (2018)
LAND4 | Newly purchased equipment to be electric, battery-powered, biofueled, or other RE-powered when commercial grade equipment is available | Yet to be addressed | Operational cost savings from reduced equipment maintenance, low GHG reduction potential, potential health benefits | Facilities | Near Term (by 2025) | Received CARB (California Air Resources Board) Grant to gain equipment in 4 primary categories: Mower(s), Blower(s), Weed-whip(s), and Pole-trimmer(s). New electric equipment has been purchased with Grant funds, however gas powered equipment is still in use.
LAND5 | Carbon sequestration: Restore native woodland to maximum extent possible on non-landscaped areas of the Hayward and Concord campuses. | In Progress | Significant ecological benefits, moderate GHG reductions; Cost implications need to be studied (possible cost benefits if offsets from sequestration are certified) | Facilities | Medium (by 2030) to Long Term (by 2040) | Projects supporting this action step are being conducted on the Concord Campus.
LAND6 | Continue turf conversion project using Bay Friendly Landscaping policies. | In Progress | Operational cost savings from energy, water, and labor savings; environmental benefits. | Facilities | Immediate (2018) | As areas need replanting, native plant species will be used.
LAND7 | Increase tree cover in parking lots and other locations on campus. Use high albedo paving surfaces (permeable where possible). | In Progress | Moderate GHG reduction potential; significant co-benefits including mitigation of heat island effect, positive aesthetic impact; significant environmental comfort and health benefits | Facilities | Near Term (by 2025) to Medium (by 2030) | In the process of doing this on various locations on campus.
LAND8 | Pursue the development of on-campus organic food production in the form of multi-cultural heritage gardens, that serve as a foundation for the sharing of multicultural food and traditions. | Yet to be addressed | Minimal GHG reduction potential; significant co-benefits | Facilities,Academic Affairs | Near Term (by 2025) to Medium (by 2030)
LAND9 | Continue to investigate the potential for on-campus composting program consisting of food waste and landscape debris with finished product for reuse as compost, landscape materials on campus. | In Progress | Low GHG reduction resulting from decreased transport of materials to waste facility and decrease in need for synthetic fertilizer; operational cost savings as finished compost used in place of purchased fertilizer | Facilities | Near Term (by 2025) | Office of Sustainability and Sustainability Ambassador Program are actively researching, developing and gaining support for an on campus composting program. A budget and proposal has been drafted, and is expected to be presented within the next Academic Year.
EDU1 | Pursue fulfillment of commitment to educate all students on carbon neutrality (per the 2007 Senate Sustainability Resolution and the President's Carbon Commitment) | In Progress | Highly significant educational impact. Moderate direct GHG reduction potential, but possibly large indirect GHG reductions through changing students behaviors and attitutudes over their lifetime. | Academic Senate | Medium Term (by 2030) | The Senate Sustainability Committee has adopoted this charge. The Committee has recommended that the Univeristy require all students to take a Carbon Neutrality Overlay course. The Executive Committee tasked the Senate Committe on Instruction and Curriculum to identify the best means to comply with that commitment. Climate change curriculum has expanded as Health Sciences have embedded climate change into core curriculum. Multiple co-curricular events around carbon neutrality issues occur throughout the academic year. Since the semester conversion, 7 courses with carbon neutral content have been introduced.
EDU2 | Facilitate student learning on climate neutrality issues through involvement in research, hands-on-learning, campus-as-a-living-laboratory, community engagement on issues of climate mitigation and adaptation, carbon-neutrality internship placements, and freshman learning communities | In Progress | Significant educational impact, especially for diverse student population, as under-represented minorities benefit most from high impact learning practices such as theses. Significant GHG reduction potential from campus-as-living-laboratory projects. | Faculty,Office of Sustainability,Center for Community Engagement | Near Term (by 2025) | Campus as a Living Lab Grant awarded to Patty Oikawa to be used for offsetting CSUEB's greenhouse gas emissions with reforestation on Concord campus. "We plan to use stipend funds to develop new courses, one focused on spatial analysis of data and reforestation design and one focused on biogeochemical measurements and modeling. In the first class, we will map existing trees on Concord campus using field trips and Google Earth Engine. The second class of students will take the date from the previous group and design a reforestation project. All following students will be involved in implementing and monitoring the reforestation project. Each year, the students will provide and estimate of the amount of carbon sequestered by the project which CSUEB can use to offset annual greenhouse gas emissions." -Patty Oikawa CSUEB was awarded a grant by the State of California's Strategic Growth Council's Climate Change Research Program to be invested in carbon sequestration activities in 'working lands'. Patty Oikawa and her students' research will be focused on rangeland on the Concord campus' Galindo Creek Field Station, where they will study the land's uptake and release of various gases. The research will center around placing compost on rangeland soils to sequester carbon out of the atmosphere in the form of carbon dioxide. According to Patty, "There has been research in this area, but we are the first to do it at the ecosystem scale." https://www.ebtoday.com/stories/working-lands CSUEB has hired alumni to fulfill Climate Corps AmeriCorps position on campus. Through their work on campus, the fellows gain experience learning about climate protection practices and develop professional skills and understanding for future work in the sustainability and climate action field. Student Sustainability Ambassadors conduct reporting for Sustainability Tracking, Assessment & Rating System™ (STARS®) and greenhouse gas inventories.
EDU3 | Include recognition of work on University ILOs in the RTP process (this indirectly supports carbon neutrality work through the Sustainability ILO) | Meeting Requirements | Moderate | Academic Senate | Immediate (2018) | 17-18 FAC 10: Revision of the Revision of RTP Procedures Semesters and for Electronic Submission of Dossiers. Based on input received by the FAC from the Senate Sustainability Committee concerning how to adequately evaluate faculty that do interdisciplinary work across departmental boundaries. The FAC recommended that the RTP document acknowledge the importance of faculty efforts to address the university Institutional Learning Outcomes (ILOs). President approved 6/27/2018.
EDU4 | Pursue an interdisciplinary sustainability minor that includes education on carbon neutrality | In Progress | Moderate but important stepping stone | Academic Senate | Near Term (by 2025) | Academic Programs and Services is working to develop a Sustainability track GE minor. A charter has been drafted to allow the Sustainability minor to act as a GE pathway. SLOs are being developed for 'Sustainable and Socially Just Communities' course category. The Senate Sustainability Committee is recommending carbon neutrality overlay.
EDU5 | Pursue faculty hires to support universal education on carbon neutrality | Yet to be addressed | Significant and essential to maintain momentum | Academic Affairs | Immediate (2018) to Long Term (by 2040)
FIN1 | Financial Analysis of Carbon Neutrality Plan An analysis of the most cost effective to achieve carbon neutrality, to account for and prioritize projects based on project implementation costs, potential long-term financial costs/benefits, and greenhouse gas reductions | Yet to be addressed | Significant: Enabler of entire Climate Action Plan | Administration and Finance Division | Near Term (by 2025)
FIN2 | Ensure Annual Budget & Staff Time for GHG-reduction efforts. Best practices include the use of an energy efficiency revolving fund in which costs savings resulting from energy efficiency improvements are reinvested in further improvements | Yet to be addressed | Significant GHG reduction impact in that this enables fulfillment of the Climate Action Plan; potentially significant energy cost savings from energy efficiency projects | Administration and Finance Division | Near Term (by 2025)
FIN3 | Incorporate the cost of carbon, along with other project costs, in the cost-benefit analysis of new infrastructure projects: Use the most recent mean price (dollars per metric ton) from the California Cap-and-Trade Program Auction. Currently available in the Summary of Results Report on the California Air Resources Board website: https://www.arb.ca.gov/cc/capandtrade/auction/auction.htm#proceeds | Yet to be addressed | Significant educational impact for staff because it serves as constant reminder to incorporate carbon neutrality in all project planning. Moderate GHG reduction potential | Facilities | Immediate (2018)
FIN4 | Divest from fossil fuel investments: (focused on companies with major investments in coal, oil, gas, and/or unconventional fossil fuels (e.g. oil shale and tar sands). Co-benefit: prudent to protect the university from excessive volatility in fossil energy prices. (see for example NYT, 3-10-2017) Amend the Cal State East Bay Education Foundation Investment Policy accordingly | Yet to be addressed | Significant educational and ethical impact. Important PR messaging impact. Moderate GHG reduction potential because of small endowment currently. Potential longer-term higher investment returns given the global shift toward alternative sustainable energy sources | Cal State East Bay Education Foundation Board of Directors | Near Term (by 2025)
OFF1 | True-up Emissions Policy. To ensure emissions reduction efforts meet targets the University will assess and true-up emissions every three years and make offset purchases as needed to meet with target. | Yet to be addressed | Significant GHG reduction potential; monetary cost savings, because offsets are only used to help achieve emissions reductions targets if the offsets cost are lower than achieving those same reductions through efficiency improvements or renewable energy. | CSC,Accounting | Near Term (by 2025)

## UMBRELLA POLICIES
Umbrella Policy | Proposed Policies | Status | 2018 Progress
UMB1 | Target: Carbon neutrality by 2040. | In Progress | Overall, 10% of the CAP Action Steps have been completed and 40% are in progress. Meeting the requirements of these Action Steps contribute to CSUEB meeting its goal to reach carbon neutrality by 2040.
UMB2 | Responsible parties will report annually on progress to meet carbon neutrality goals | Meeting Requirements
UMB3 | Carbon Management Hierarchy: Consistent with Second Nature's guidance for the development and implementation of climate action plans, the priority order for emissions is (1) reduce emissions with energy efficiency and conservation, (2) replace carbon energy sources with renewable energy, (3) neutralize emissions with offsets | In Progress | Facilities Development & Operations is working within the Division of Administration and Finance to complete a Request for Proposals (RFP) to select a vendor to conduct an energy efficiency assessment for CSUEB (see ENG1, below) and implement “Solar IV,” the Chancellor's Office System-Wide Solar Photovoltaic Program Master Enabling Agreement.
UMB4 | The University will review, revise if necessary, and submit the climate action plan to Second Nature no less frequently than every five years | Yet to be Addressed
UMB5 | Annually the University will complete an evaluation of progress and submit to Second Nature | Meeting Requirements
UMB6 | Integrate Climate Action Planning into other campus policies: e.g. Master Plan | Yet to be Addressed
UMB7 | The university will take a life-cycle planning approach to major projects. | Yet to be Addressed
UMB8 | Leverage partnership opportunities to reduce GHG emissions at least cost and greatest benefit (e.g. with the CSU, the City of Hayward, the County of Alameda) | In Progress | CSUEB works in collaboration with the City of Hayward on the Campus Sustainability Committee (CSC), as the City’s Environmental Services Manager is an ex-officio member of the CSC. Pioneer Heights has switched its energy provider from PG&E to East Bay Community Energy (EBCE), a Community Choice Aggregation (CCA), which sources a cleaner grid mix.

## ENERGY
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
ENG1 | Develop and maintain an operation and maintenance plan to reduce energy use, maximize equipment efficiency, and most effectively utilize deferred maintenance funds. (The Campus will prioritize facilities upgrades that reduce operating costs and replace equipment at end of life. The campus energy team will engage in an ongoing process to seek opportunities to improve energy efficiency using energy monitoring data, periodic energy audits, continuous commissioning) | In Progress | Significant GHG reduction potential; significant operational cost savings | Facilities | Near Term (by 2025) | Facilities Development & Operations is working with the Division of Administration and Finance to complete a Request for Purchase (RFP) to select a vendor to conduct an energy efficiency assessment for CSUEB. Energy assessment will provide a baseline of energy use and be used to assess savings for Solar IV
ENG2 | Install 680 kW of new PV, or other renewable energy capacity annually (or acquire 1.2 million kWh more of RE from the power grid each year, or some combination of the two) | In Progress | Significant GHG reduction potential; potentially cost neutral | Facilities | Immediate (2018) to Long Term (by 2040) | Facilities Development & Operations is working with the Division of Administration & Finance and the Chancellor's Office on Solar IV: System-Wide Solar Photovoltaic Program Master Enabling Agreement (MEA) at CSU East Bay.
ENG3 | Prioritize PV installations to: displace all Concord Campus Energy use (~630kW), on Hayward Campus parking lots (~8MW long term) | Yet to be addressed | Significant GHG reduction potential | Facilities | Immediate (2018) to Long Term (by 2040)
ENG4 | Install PV system of a size necessary to displace annual electricity use of the Concord Campus | Yet to be addressed | Very significant GHG reduction potential; low to moderate equipment cost with potential for RECs; significant educational opportunity | Facilities,Admin | Near Term (by 2025)
ENG5 | Prioritize purchase of high renewable powercontent, low unspecified power content, grid power. Pursue possibility of aggregated group purchase of off-site renewable energy with other CSU campuses, the City of Hayward, or the County of Alameda | In Progress | Significant GHG reduction potential; cost of power may be higher than current contract in the near term | Facilities,Admin | Near Term (by 2025) | CSU East Bay Housing has been converted to East Bay Community Energy (EBCE), a local electricity provider that procures electricity from clean, renewable sources such as solar and wind. "EBCE reinvests earnings back into the community to create local green energy jobs, local programs, and clean power projects." Source: https://ebce.org
ENG6 | Institute on-going energy management training of building technicians | Meeting Requirements | Significant operational cost savings and GHG reduction potential | Facilities | Immediate (2018) | Staff in facilities are trained in the daily operation, repair and maintenance of the several building management systems in each building. Energy management is achieved through the optimization and efficiency of mechanical, electrical and plumbing systems using defined programs controlling the following: HVAC equipment schedules Lighting schedules Low water volume plumbing fixtures Sprinkler schedules Solar panel support equipment maintenance Fuel Cell waste water On-going training attended is as follows: Certified Pool Operator certification Building Operator Certificate certification Chiller/Boiler training/certification Vendor specific building management training/certification Lighting Automation training
ENG7 | The campus information technology team will maintain all campus-owned computers, displays, and related technology to always operate in energy saver mode, unless needed for a documented exception. | In Progress | Low to moderate operational cost savings and GHG reduction potential | IT | Near Term (by 2025) | When computer monitors are configured they will typically go into energy saver mode after a period of non-usage. TV monitors used in classrooms and conference rooms are controlled by a single platform that will turn them off at night. Projectors in classrooms are turned off if not in use.
ENG8 | Research emerging energy technologies for carbon savings (e.g. PV-source heat pump replacing natural gas, thermal energy storage) | Yet to be addressed | Possibly significant GHG reduction potential | Faculty | Near Term (by 2025)
ENG9 | Investigate the potential for Cal State East Bay wind-power facilities | In Progress | Low to moderate GHG reduction potential; moderate educational value | Facilities | Medium Term (by 2030) | As part of Physics 3999 in Spring 2017 led by Dr. Ryan Smith, a wind monitoring study was done on North Science Building by students Michael Norcross & Michael Kronic which suggested average wind speeds did not meet the required wind speed to move a typical low wind speed turbine. Based on their collected data, they recommended the installation of solar panels be perused on Hayward Campus instead of wind turbines. Wind energy generation may be more feasible on Concord Campus.

## TRANSPORTATION
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
TRAN1 | Increase online coursework and opportunities for telework | Yet to be addressed | Significant GHG reduction potential | Academic Affairs,IT | Immediate (2018) to Long Term (by 2040)
TRAN2 | Enhance and encourage the use of alternative transportation modes | In Progress | Significant GHG reduction potential | Transportation Planning | Immediate (2018) | A Request for Proposals (RFP) for a new shuttle contract was issued in March 2019. The new shuttle contract allows the opportunity to add additional shuttles to meet higher ridership demands, as needed. Bids received from the RFP will allow for better decision making on whether or not to continue using shuttles or switching service to AC Transit. Transportation has plans to increase collaboration with Associated Students, Inc. (ASI). In order to promote alternative transportation programs at CSUEB, Transportation will table more often during U-hour (T/TH 12:15 - 1:15). At tabling events, students will have the opportunity to sign up for alternative transportation programs in exchange for CSUEB swag.
TRAN3 | Pursue subsidized transit passes for students, staff, and faculty (including AC transit and BART) | In Progress | Moderate to significant GHG reduction potential | Transportation Planning | Near Term (by 2025) | Procurement is currently in discussions with AC Transit about AC Transit providing exclusive service to the Hayward campus. This would be free for students, faculty, and staff on all AC transit routes, including Transbay, 7 days per week. An RFP was issued for Shuttle Services (in the event that an agreement with AC Transit does not materialize). Responses are due back at the end of April 2019, and will be evaluated. It is expected that by July 2019 CSU East Bay shall be able make the determination which one of the following three options are best for the campus: (i) Contracting with AC Transit, (ii) Awarding a contract for a shuttle provider, or (iii) Piggybacking off of a University of California Merced contract award and use the hourly rates established under that contract for CSU East Bay.
TRAN4 | Encourage the use of alternative transportation modes with faculty and staff by implementing an Employee Cash Out Program (offer cash instead of a subsidized parking pass) | Yet to be addressed | Moderate GHG reduction potential; low cost depending on the conditions of the plan; potential employee co-benefits (health, financial, job satisfaction) | Admin,Finance | Near Term (by 2025)
TRAN5 | Offset carbon emissions from all study abroad and international travel by 2022: investigate adding the cost to the program fee that covers carbon emissions from airfare to and from the origin/destination city. | Yet to be addressed | Moderate to significant GHG reduction potential; no cost implications | Admissions,University Extension | Near Term (by 2025)
TRAN6 | All state-funded travel will be carbon neutral or 100% offset by 2022 | In Progress | Low GHG reduction potential; but more predicable outcome than most transportation measures and high education value for the university community | Admin,Finance | Near Term (by 2025) | CSU East Bay's Climate Corps Fellow has been researching methods of offsetting emissions resulting from Directly Financed Air Travel. In order to develop a policy recommendation for CSUEB, the Climate Corps Fellow has used Second Nature's Carbon Pricing Toolkit and researched programs that other Universities are piloting where a cost of carbon is added to their Business travel to offset the resulting emissions. The recommendation proposes a CSUEB Carbon Neutral State Funded Air Travel Policy, which includes: Assessing a minimal cost of carbon to all directly financed air travel and using the funds to either purchase verified carbon offsets, or reinvest the funds in on-campus projects that provide measurable reductions in Greenhouse gas emissions. The research and proposal ideas were presented at the Campus Sustainability Committee meeting in April. Based on the positive feedback received, a policy recommendation is being drafted.
TRAN7 | No net increase in the number of parking spaces for fossil-fueled vehicles. | Meeting Requirements | Moderate GHG emissions reduction potential | Facilities | Immediate (2018) | In 2018 there have not been any additional parking spaces added on campus for fossil fueled vehicles.
TRAN8 | Maintain at least 50% greater EV charging station capacity (relative to total number of parking spaces) than the statewide EV vehicle proportion as reported by the state. So, for example, if 10% of the state's onroad fleet is EVs, then 15% or our parking spaces will be for EVs. | In Progress | Low to moderate GHG reduction potential; potential educational value | Parking | Near Term (by 2025) to Long Term (by 2040) | Hayward Campus currently has 25 EV charging stations, which can accommodate 50 EVs, 50 EV parking spaces, and 10 EV waiting spaces. Lot A on Hayward Campus is expecting to convert 5 parking spaces to EV waiting spaces. On Concord Campus, 4 EV charging stations are expected to be installed in Summer 2019.
TRAN9 | All new-to-campus fleet vehicles must be electric, bio-fueled, or other RE-powered | Yet to be addressed | Low GHG reduction, reduced operational costs | Procurement | Immediate (2018)
TRAN10 | No personal vehicle/parking passes for first year residence hall students: supplement with electric or other ultra-efficient car-share vehicles | Yet to be addressed | Low direct GHG reduction potential but sets the habit of becoming more comfortable with relying on alternative transportation | Admin | Near Term (by 2025)

## BUILDINGS
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
BLDG1 | Design all new buildings to be Zero Net Energy (ZNE) starting immediately. The design process will consider the criteria and potential certification under the following: LEED, Living Building Challenge, Passive House Institute US | In Progress | Significant operational cost savings and GHG reduction potential over lifetime of building | Facilities | Immediate (2018) | There have been no new buildings constructed on campus from May 2018-May 2019. The CORE Building is designed to be ZNE ready, it will have the infrastructure for a future solar system when funding is available.
BLDG2 | No new natural-gas consuming equipment for space and water conditioning starting in 2022. For example, solar thermal systems, PV-driven heat pump systems, or off-set. | In Progress | Significant GHG reduction potential | Facilities,Procurement | Near Term (by 2025) | Chancellor's Office is discussing and developing guidance on eliminating natural gas use on campuses.
BLDG3 | Replace space heating, water heating, and cooking equipment with ultra efficient fossil-fuel-free technologies (e.g. heat pump technology) | Yet to be addressed | Significant GHG reduction potential | Facilities,Procurement | Long Term (by 2040)
BLDG4 | Maximize PV production on all new buildings. | Yet to be addressed | Moderate GHG reduction potential, cost savings over lifetime of system | Facilities | Immediate (2018)
BLDG5 | Track building energy performance with computerized monitoring systems (building energy-use monitoring) to enable more effective building energy management and GHG emissions reductions tracking [1] | In Progress | Moderate GHG reduction potential, moderate operational cost savings from more effective energy use | Facilities | Near Term (by 2025) | The Facilities Department has developed spreadsheets, using the baseline year of 2013 to evaluate progress made on eliminating GHG on campus. Facilities has continued to refine energy information received from the energy and building management systems to inform efficient building operations to meet the campus's GHG reduction goals.
BLDG6 | Post climate action educational display prominently in all main buildings. Signage will state Cal State East Bay's climate neutrality goal, and graphically display the building's progress thereto, starting with the baseline monitoring year. Longer term goal to incorporate real-time dashboard of overall GHG savings on main buildings | Yet to be addressed | Significant educational and motivational impact | Facilities | Near Term (by 2025)

## HOUSING
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
HOUS1 | Switch to Solar Water Heating in Pioneer Heights. Investigate options (solar thermal collectors versus PV). | Yet to be addressed | Significant reduction in natural gas demand in residence halls and associated GHG reductions (currently N-gas accounts for 60% of the Hayward Campus's residence hall energy use.) | Facilities | Near Term (by 2025)
HOUS2 | Institute policy to increase campus housing to 5,000 student residents by 2032 and encourage first year students to live in residence halls (consistent with master plan) | Yet to be addressed | Significant GHG reduction potential from both commuting and zero net energy housing, but increases the challenge of achieving carbon neutrality; potential increase in water use on campus | Admin | Long Term (by 2040)
HOUS3 | Investigate potential for building low-cost faculty housing on or near campus. Co-benefit of attracting qualified faculty on state salary given prohibitive Bay Area housing prices | Yet to be addressed | Moderate GHG reduction potential from commuting and zero net energy housing, but increases the challenge of achieving carbon neutrality; potential increase in water use on campus; potentially significant co-benefits in attracting and retaining new faculty | Admin | Near Term (by 2025)

## PROCUREMENT
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
PROC1 | Adopt Electronics and Appliance Procurement Policy (in progress) that requires: Bronze EPEAT® or higher for EPEAT®-rated products, ENERGY STAR® for everything else if available, and Suppliers to deliver electronics with conservation and energy efficiency features enabled and as the auto-default | Meeting Requirements | Moderate GHG reduction potential, moderate operational cost savings | Procurement | Immediate (2018) | Draft policy is complete and in use on campus. Waiting on "Policy on policies" to formally adopt. Procurement has been incorporating a sustainability blurb in the P-card Policy. The sustainability blurb is a broad statement that covers multiple sustainable procurement sectors. Includes the following statement, "Ordering energy efficient electronics should be considered in all purchasing." The statement also directs the reader to CSUEB's Sustainability website.
PROC2 | Initiate accounting of carbon emissions from procurement (e.g. using the Economic Input-Output Life Cycle Assessment (EIP-LCA) tool) | Yet to be addressed | Significant GHG reduction potential | Procurement | Near Term (by 2025)
PROC3 | Investigate policy for locally sourcing materials to reduce transportation energy use associated with procurement. E.g. Purchase majority of construction materials within 250 miles | In Progress | Moderate GHG reduction potential, potential for higher cost of goods | Procurement | Near Term (by 2025) | Procurement has been incorporating a sustainability blurb in the P-card Policy. The sustainability blurb is a broad statement that covers multiple sustainable procurement sectors. Includes section that states the selection of vendors should consider distance and minimization of number of deliveries.
PROC4 | Establish 100% Recycled Copy/Print Paper Policy (in progress) | Meeting Requirements | Low GHG reduction potential; increased cost of paper | Procurement | Immediate (2018) | Draft policy is complete and in use on campus. Waiting on "Policy on policies" to formally adopt.
PROC5 | Continue to move away from the use of paper-based processes with digital processes | In Progress | Low GHG reduction potential; moderate monetary cost savings potential | Procurement | Near Term (by 2025) | CSUEB is in the process of implementing the fully electronic Certify Reimbursement System, which moves the reimbursement process completely away from paper processes. A pilot program will launch in April 2019 beginning with A & F, if it is successful this program will launch campus wide. CSUEB has adopted the Adobe Sign program, removing the need for paper signatures.

## LANDSCAPING
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
LAND1 | The university will adopt SITES certification criteria in developing landscaping projects | Yet to be addressed | Moderate general environmental benefits | Facilities | Near Term (by 2025)
LAND2 | The university will adopt Bay Friendly Landscaping practices | Yet to be addressed | Moderate operational cost savings from energy, water, and labor reductions; moderate GHG reduction potential; environmental benefits. | Facilities,CSC | Near Term (by 2025)
LAND3 | University will discontinue use of synthetic fertilizers within 5 years | Yet to be addressed | Minimal GHG emissions reduction, moderate general environmental and health benefits, significant symbolic impact | Facilities | Immediate (2018)
LAND4 | Newly purchased equipment to be electric, battery-powered, biofueled, or other RE-powered when commercial grade equipment is available | Yet to be addressed | Operational cost savings from reduced equipment maintenance, low GHG reduction potential, potential health benefits | Facilities | Near Term (by 2025) | Received CARB (California Air Resources Board) Grant to gain equipment in 4 primary categories: Mower(s), Blower(s), Weed-whip(s), and Pole-trimmer(s). New electric equipment has been purchased with Grant funds, however gas powered equipment is still in use.
LAND5 | Carbon sequestration: Restore native woodland to maximum extent possible on non-landscaped areas of the Hayward and Concord campuses. | In Progress | Significant ecological benefits, moderate GHG reductions; Cost implications need to be studied (possible cost benefits if offsets from sequestration are certified) | Facilities | Medium (by 2030) to Long Term (by 2040) | Projects supporting this action step are being conducted on the Concord Campus. (See Action Step progress reported on EDU2)
LAND6 | Continue turf conversion project using Bay Friendly Landscaping policies. | In Progress | Operational cost savings from energy, water, and labor savings; environmental benefits. | Facilities | Immediate (2018) | As areas need replanting, native plant species will be used.
LAND7 | Increase tree cover in parking lots and other locations on campus. Use high albedo paving surfaces (permeable where possible). | In Progress | Moderate GHG reduction potential; significant co-benefits including mitigation of heat island effect, positive aesthetic impact; significant environmental comfort and health benefits | Facilities | Near Term (by 2025) to Medium (by 2030) | In the process of doing this on various locations on campus.
LAND8 | Pursue the development of on-campus organic food production in the form of multi-cultural heritage gardens, that serve as a foundation for the sharing of multicultural food and traditions. | Yet to be addressed | Minimal GHG reduction potential; significant co-benefits | Facilities,Academic Affairs | Near Term (by 2025) to Medium (by 2030)
LAND9 | Continue to investigate the potential for on-campus composting program consisting of food waste and landscape debris with finished product for reuse as compost, landscape materials on campus. | In Progress | Low GHG reduction resulting from decreased transport of materials to waste facility and decrease in need for synthetic fertilizer; operational cost savings as finished compost used in place of purchased fertilizer | Facilities | Near Term (by 2025) | Office of Sustainability and Sustainability Ambassador Program are actively researching, developing and gaining support for an on campus composting program. A budget and proposal has been drafted, and is expected to be presented within the next Academic Year.

## EDUCATION
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
EDU1 | Pursue fulfillment of commitment to educate all students on carbon neutrality (per the 2007 Senate Sustainability Resolution and the President's Carbon Commitment) | In Progress | Highly significant educational impact. Moderate direct GHG reduction potential, but possibly large indirect GHG reductions through changing students behaviors and attitutudes over their lifetime. | Academic Senate | Medium Term (by 2030) | The Senate Sustainability Committee has adopoted this charge. The Committee has recommended that the Univeristy require all students to take a Carbon Neutrality Overlay course. The Executive Committee tasked the Senate Committe on Instruction and Curriculum to identify the best means to comply with that commitment. Climate change curriculum has expanded as Health Sciences have embedded climate change into core curriculum. Multiple co-curricular events around carbon neutrality issues occur throughout the academic year. Since the semester conversion, 7 courses with carbon neutral content have been introduced.
EDU2 | Facilitate student learning on climate neutrality issues through involvement in research, hands-on-learning, campus-as-a-living-laboratory, community engagement on issues of climate mitigation and adaptation, carbon-neutrality internship placements, and freshman learning communities | In Progress | Significant educational impact, especially for diverse student population, as under-represented minorities benefit most from high impact learning practices such as theses. Significant GHG reduction potential from campus-as-living-laboratory projects. | Faculty,Office of Sustainability,Center for Community Engagement | Near Term (by 2025) | Campus as a Living Lab Grant awarded to Patty Oikawa to be used for offsetting CSUEB's greenhouse gas emissions with reforestation on Concord campus. "We plan to use stipend funds to develop new courses, one focused on spatial analysis of data and reforestation design and one focused on biogeochemical measurements and modeling. In the first class, we will map existing trees on Concord campus using field trips and Google Earth Engine. The second class of students will take the date from the previous group and design a reforestation project. All following students will be involved in implementing and monitoring the reforestation project. Each year, the students will provide and estimate of the amount of carbon sequestered by the project which CSUEB can use to offset annual greenhouse gas emissions." -Patty Oikawa https://www.ebtoday.com/stories/working-lands CSUEB was awarded a grant by the State of California's Strategic Growth Council's Climate Change Research Program to be invested in carbon sequestration activities in 'working lands'. Patty Oikawa and her students' research will be focused on rangeland on the Concord campus' Galindo Creek Field Station, where they will study the land's uptake and release of various gases. The research will center around placing compost on rangeland soils to sequester carbon out of the atmosphere in the form of carbon dioxide. According to Patty, "There has been research in this area, but we are the first to do it at the ecosystem scale." -Patty Oikawa https://www.ebtoday.com/stories/working-lands CSUEB has hired alumni to fulfill Climate Corps AmeriCorps position on campus. Through their work on campus, the fellows gain experience learning about climate protection practices and develop professional skills and understanding for future work in the sustainability and climate action field. Student Sustainability Ambassadors conduct reporting for Sustainability Tracking, Assessment & Rating System™ (STARS®) and greenhouse gas inventories.
EDU3 | Include recognition of work on University ILOs in the RTP process (this indirectly supports carbon neutrality work through the Sustainability ILO) | Meeting Requirements | Moderate | Academic Senate | Immediate (2018) | 17-18 FAC 10: Revision of the Revision of RTP Procedures Semesters and for Electronic Submission of Dossiers. Based on input received by the FAC from the Senate Sustainability Committee concerning how to adequately evaluate faculty that do interdisciplinary work across departmental boundaries. The FAC recommended that the RTP document acknowledge the importance of faculty efforts to address the university Institutional Learning Outcomes (ILOs). President approved 6/27/2018.
EDU4 | Pursue an interdisciplinary sustainability minor that includes education on carbon neutrality | In Progress | Moderate but important stepping stone | Academic Senate | Near Term (by 2025) | Academic Programs and Services is working to develop a Sustainability track GE minor. A charter has been drafted to allow the Sustainability minor to act as a GE pathway. SLOs are being developed for 'Sustainable and Socially Just Communities' course category. The Senate Sustainability Committee is recommending carbon neutrality overlay.
EDU5 | Pursue faculty hires to support universal education on carbon neutrality | Yet to be addressed | Significant and essential to maintain momentum | Academic Affairs | Immediate (2018) to Long Term (by 2040)

## FINANCE
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
FIN1 | Financial Analysis of Carbon Neutrality Plan An analysis of the most cost effective to achieve carbon neutrality, to account for and prioritize projects based on project implementation costs, potential long-term financial costs/benefits, and greenhouse gas reductions | Yet to be addressed | Significant: Enabler of entire Climate Action Plan | Administration and Finance Division | Near Term (by 2025)
FIN2 | Ensure Annual Budget & Staff Time for GHG-reduction efforts. Best practices include the use of an energy efficiency revolving fund in which costs savings resulting from energy efficiency improvements are reinvested in further improvements | Yet to be addressed | Significant GHG reduction impact in that this enables fulfillment of the Climate Action Plan; potentially significant energy cost savings from energy efficiency projects | Administration and Finance Division | Near Term (by 2025)
FIN3 | Incorporate the cost of carbon, along with other project costs, in the cost-benefit analysis of new infrastructure projects: Use the most recent mean price (dollars per metric ton) from the California Cap-and-Trade Program Auction. Currently available in the Summary of Results Report on the California Air Resources Board website: https://www.arb.ca.gov/cc/capandtrade/auction/auction.htm#proceeds | Yet to be addressed | Significant educational impact for staff because it serves as constant reminder to incorporate carbon neutrality in all project planning. Moderate GHG reduction potential | Facilities | Immediate (2018)
FIN4 | Divest from fossil fuel investments: (focused on companies with major investments in coal, oil, gas, and/or unconventional fossil fuels (e.g. oil shale and tar sands). Co-benefit: prudent to protect the university from excessive volatility in fossil energy prices. (see for example NYT, 3-10-2017) Amend the Cal State East Bay Education Foundation Investment Policy accordingly | Yet to be addressed | Significant educational and ethical impact. Important PR messaging impact. Moderate GHG reduction potential because of small endowment currently. Potential longer-term higher investment returns given the global shift toward alternative sustainable energy sources | Cal State East Bay Education Foundation Board of Directors | Near Term (by 2025)

## OFFSETS
Action Step Title | Action Step Description | Status | Estimated Impact | Leadership | Timeline | 2018 Progress
OFF1 | True-up Emissions Policy. To ensure emissions reduction efforts meet targets the University will assess and true-up emissions every three years and make offset purchases as needed to meet with target. | Yet to be addressed | Significant GHG reduction potential; monetary cost savings, because offsets are only used to help achieve emissions reductions targets if the offsets cost are lower than achieving those same reductions through efficiency improvements or renewable energy. | CSC,Accounting | Near Term (by 2025)